## Sheet1
Priority goals | May 2020 | July 2020 | August 2020 | September 2020 | October 2020 | November -December 2020
Detailed educational syllabus (detailed modules) for practicing non-BV valuers | EBVSB Electronic communication, proposal of the agenda 2020-2024. Video meeting Sub group by the end of the May; shareout of the work; exact date to be confirmed | Video meeting Sub group by the end of July, excat date to be confirmed; discussion of the first draft which is delivered one week prior to the meeting. | Video meeting Sub group and representative of iiBV; exact date to be confirmed; agreement on the first draft of the syllabuses | Video meeting EBVSB (if possible due to the large number of members) or electronic communication- presentation of the syllabus; exact date to be confirmed; discussion; invitation to send comments and proposals | EBVSB Electronic communication and agreement on the drafted syllabuses as work in progress, which will be presented at the GA. Meeting in Brussels to discuss in live the syllabuses and overal requirements for TEGoVA BV professional designation. | Further development of syllabuses, Sub group electronic communication
Detailed educational syllabus (detailed modules) for BV practicing individuals
Priority goals | January 2021 | February 2021 | March 2021 | April 2021 | May 2021
Requirements relating to the education (depending on the individual’s background) for TEGoVA BV professional designation Requirements relating to the experience for TEGoVA BV professional designation | Video meeting Sub group by the end of the January; summary of the work on syllabuses. Shareout of the work on requirements; exact date to be confirmed | Video meeting Sub group by the end of February, exact date to be confirmed; discussion of the first draft on requirements which is delivered one week prior to the meeting. | Video meeting EBVSB (if possible due to the large number of members) or electronic communication- presentation of the last version of the syllabuses; presentation of the first draft on requirements; exact date to be confirmed; discussion; invitation to send comments and proposals | Video meeting EBVSB or electronic communication, exact date to be confirmed; discussion on requirements and syllabuses | EBVSB electronic communication and agreement on the draft of requirements which will be presented at the GA and any changes on the syllabuses. Meeting in Brussels to discuss other goals and shareout of work in groups (2-3 working groups).